## Attendance
Date | Nick | Danny | Theo | Phillip | Sam | Steve
2020-01-30 | [6 empty] | Green = Attendance
2020-02-05 | [6 empty] | Yellow = Reason Given
2020-02-11 | [6 empty] | Red = No show
2020-02-19 | [6 empty] | WFH = Work from home
2020-02-24
2020-02-25 |  |  | WFH
2020-02-27
2020-02-28
2020-03-06

## Agile Scrum Plan
Agile Scrum Plan
Date/Time | Scrum | Retrospect | Sprint Review | Project Owner | Theo | Retrospect = Did we do it
Week 4/ Jan | Started research on FSM | Yes | We successfully researched FSM using different sources and Looked at multiple strategies of implementation | Scrum Master | Nikesh | Sprint review = How well did we do it and what could be better
| Started planing scrum plan | Yes | We colour coded each week to correctly divide the different parts of the assignment plan, found no issues | Lead Designer | Steve
Week 1/Feb | Started generating pseudocode | Yes | We created a lot of pseudocode for the FSM states, which we can now impliment into the project | Lead Tester | Sam
Week 2/ Feb | Created rules for FSM | Yes | Created rules for each of the states and the varying types of tanks | Report Planner | Danny
| Started report | Yes | We started the introduction with the explanation of the FSM with also the project management | Scrum Planner | Phil
Week 3/ Feb | Create OOP FSM | Yes | We have created the FSM however bugs need to be managed
| Fixing bugs for FSM | Yes | Managed to patch the issues after creating the FSM
| Creating states: Idle | Yes | Finished with the Idle states so now the tank stays Idle
Week 4/ Feb | Creating states: Patrol | Yes | Finished with the patrolling state, now the tank can patrol around the map
| Creating states: Attack Enemy | Yes | Finished the Attack Enemy state, the tank can now switch states and focus on attack
| Creating states: Collect consum | Yes | Introduced the states for finding consumables, the tank focuses on consumables when they are seen
Week1/Mar | Creating states: Finding Cover | Yes | We added the finding cover states, the tank now retreats to waypoints away from the dumbtank
| Creating states: Defend Base | Yes | The final state, Defend Base is added with the other states
Week 2/ Mar | Changing Finding cover to flee | Yes | We were having issues with the Finding cover states so we changed the states to flee instead
| Working on fixing states | Yes | Fixing the bugs in the code with looking for better ways to layout the code
Week 3/ Mar | Implement the FSM | Yes | After all the bugs and Issues were resolved, we could now finally implement it
| Testing out the tanks | Yes | Now we can do testing on the tanks Ai to see the performance
Week 4/ Mar | Writing up documents | Yes | Wrote up the report and the presentation with also the different paperwork necessary
Demonstration Week

## Gantt Chart
Project Step | Week 4 January | Week 1 Februray | Week 2 February | Week 3 February | Week 4 February | Week 1 March | Week 2 March | Week 3 March | Week 4 March | Due 27/03
Research and Development
Generating Pseudocode
Class Design
Designing the Finite State
Creating the Finite State
Creating Idle State
Create Patrol State
Create Attack Enemy State
Create Find Cover State
Create Collect Consumables State
Create Defend Base State
Implementing the Finite State
Scrum Plan
Bug Fixes
Testing
Writeup